NOAA Climate Test Bed (CTB)

Part I. Science Plan and Implementation Strategy

Part II. Management and Operations Plan

CTB Management Team - Wayne Higgins (NOAA/Climate Prediction Center)

Hualu Pan (NOAA/Environmental Modeling Center)

Melvyn Gelman (NOAA/Climate Prediction Center)

Ming Ji (NOAA/Climate Program Office)

NOAA CTB Science Plan & Implementation Strategy

NOAA CTB Management and Operations Plan

_____________________________________________________________________________

January 2007

Table of Contents										               Page

EXECUTIVE SUMMARY	4

PART I.  SCIENCE PLAN AND IMPLEMENTATION STRATEGY	7

1.0 SCIENCE PLAN	7

1.1 Vision and Mission	7

1.2 Relationship to NOAA Strategic Plan	8

1.3 Objectives	10

1.4 Requirements to Improve Climate Prediction	10

1.5 Programmatic and Science Priorities	13

2.0 IMPLEMENTATION STRATEGY	14

2.1 Transition Project Teams	14

2.2 Strategy and Current Activities	15

3.0 SCIENTIFIC PARTNERSHIPS	19

4.0 TECHNOLOGY TRANSFER	22

4.1 Types of Transition	22

4.2 Transition Guidelines	23

4.3 Data Policy and Access	23

4.4 Communicating Results	24

5.0 PROGRESS ASSESSMENT	25

5.1 Performance Objectives	25

5.2 Expected Outcome	26

6.0 REFERENCES	26

PART II.  MANAGEMENT AND OPERATIONS PLAN	27

1.0 FRAMEWORK	27

1.1 Infrastructure	27

1.2 Transition Projects	28

1.3 Facility	28

1.4 Organization	28

2.0 STAFF	29

3.0 FUNDING	29

4.0 COMPETITIVE TRANSITION PROJECTS	29

4.1 Initiation Procedure	29

4.2 Computer Resources Request	30

4.3 Computer Access	30

4.4 Data Policy and Access	31

4.5 Conflicts of Interest	31

Page

5.0 ANNUAL OPERATING PLAN	32

5.1 NTOPs	32

5.2 Milestones	32

5.3 Budget	32

5.4 Meetings	33

5.5 Reports	34

5.6 Webpage	34

Appendix A.  Research to Operations Guidelines	35

Appendix B.  Operations to Applications Guidelines	40

Appendix C.  Management Structure and Terms of Reference	41

Appendix D.  Proposed Timeline for next CFS Implementation	47

Appendix E.  Contact Information	48

Appendix F.  Acronyms	49

Executive Summary

NOAA/NCEP is the lead agency with responsibility for improving our Nation’s operational climate predictions on time scales ranging from weeks to years.  Improvements in predictions are envisioned in the coming years that will lead to “A Seamless Suite of Forecasts” spanning weather, intraseasonal, interannual, and multi-decadal timescales.  The mission of the CTB is to facilitate this outcome by accelerating the transition of scientific advances from the climate research community to improved NOAA climate forecast products and services.  This document describes the CTB science plan and the associated implementation strategy.

The science plan is intended to be a living document which we will continue update and  vet with the community.  The current plan was developed in consultation with the National Centers for Environmental Prediction (NCEP) and the NOAA Climate Program Office (NCPO) to ensure that it is consistent with the relevant NOAA Mission and Support Goals encapsulated here in terms of four programmatic priorities for improved climate prediction consisting of:

- Multi-Model Ensemble Prediction System

- Climate Forecast System Improvements

- Climate Forecast Products

- Climate Reanalysis

The CTB science plan recognizes that progress must be made in each of these four areas.  Specifically, the CTB must foster improvements in CFS by accelerating the transition of the relevant process level advances in NCEP’s weather prediction model (the Global Forecast System or GFS) to CFS, and by supporting targeted research and development by the science community.  These advances must be integrated and fully validated in CFS; a critical step that requires long-term reanalysis data.  Reanalysis data are also required for calibrating the CFS predictions, and for integrating them with other forecasting tools using a multi-model ensemble approach that ultimately combines all known sources of independent skill.  The development of a multi-model ensemble prediction system is a top priority for CTB.  Finally, the science plan recognizes that the development of new and improved climate forecast products, including consolidated forecasts and regional products, is a fundamental aspect of the transition to applications for decision support.  This includes the development of improved drought monitoring and prediction products for user applications, including the National Integrated Drought Information System (NIDIS).

A list of potential science priority areas that the CTB endorses is given below for each programmatic theme.  It is important to emphasize that the CTB is not (and cannot be) active in all of these areas: priorities will be developed and evolve over time as outlined in the implementation strategy.

Climate Forecast System (CFS) Improvements

- Accelerate assessment and development plans for CFS (ocean model and assimilation; land surface model and assimilation; physics; resolution)

- Diagnose biases in CFS/GFS and develop strategies to reduce them.

- Seek venues and resources that enable partnerships between NCEP modelers and the research community on future improvements to the CFS/GFS;

- Develop hardware/software tools and data policy for disseminating climate information on publicly accessible server;

- Develop a standard diagnostics package for CFS assessments;

- Participate in field experiments and work with the various Climate Process Teams to improve CFS physics.

Multi-Model Ensemble Prediction System

- Establish a systematic community based multi-model forecasting capability & infrastructure using both National and International models;

- Establish sources and limits of predictability and skill on intraseasonal, seasonal and interannual timescales;

- Develop dynamical understanding of trends;

- Improve forecasts of weather – climate connection;

- Seek partnerships with other international multi-model programs.

Climate Forecast Products

- Improve and strengthen basic predictand products;

- Develop verification statistics for official and experimental forecast products and tools;

- Consolidation of multi-method seasonal forecasts;

- Drought monitoring and prediction in support of NIDIS;

- Facilitate interactions between NCEP, Regional Integrated Sciences and Assessments (RISA’s) and Applied Research Centers (ARCS).

Climate Reanalysis

- Develop implementation plans for on-going analysis of the climate system (data archaeology and stewardship; real-time analysis and monitoring; periodic reanalysis; data dissemination; applied research; forecast verification; development of operational statistical models);

- Coordination of reanalysis activities within NOAA, across agencies and  internationally.

CTB is working with NCEP/NOAA Management and the external community to focus near term priorities for each of the programmatic themes, except for reanalysis, which may be included in the future if funding is available.

The “Transition Project Teams” are the functional core of the CTB.  The teams play a central role in the CTB internal and competitive projects.  In particular, they are responsible for coordinating and completing CTB experiments and for enhancing collaboration between CTB staff and external PIs.

This plan will continue to be a living document that will evolve to a Science and Implementation plan as CTB mission requirements and capabilities are refined and established.  In the future we plan to highlight the CTBs most recent scientific accomplishments, the most important new or emerging areas of interest to NOAA, and the extent of collaborations between CTB and the external community.  Much of this information will be presented at annual Science Advisory Board, and (possibly in the future) at Principal Investigator (PI) meetings.

Part II of this document is the CTB Management and Operations Plan, which provides details on the CTB organization and institutional framework that has been put in place to achieve the CTB objectives.

For additional information on the CTB, including a “White Paper” and  “Terms of Reference” documents, the reader is referred to the CTB webpage: http://www.cpc.ncep.noaa.gov/products/ctb.

PART I.  SCIENCE PLAN AND IMPLEMENTATION STRATEGY

1. SCIENCE PLAN

In 2004 NOAA’s National Centers for Environmental Prediction (NCEP) and  Climate Program Office (NCPO; formerly Office of Global Programs) jointly established a Climate Test Bed (CTB) facility to accelerate the transition of research and development into improved NOAA climate forecasts, products and applications.    The CTB strategy, which centers around its vision and mission (see section 1.1), is closely aligned with the NOAA Climate Program, and strongly linked at this time to the Climate Predictions and Projections (P&P) component of the Program.

The CTB facility provides an operational infrastructure (computing support, Transition Project Teams (TPTs), and competitively-funded transition projects) to accelerate improvements in NOAA climate predictive capabilities, with an increased range of applicability for management and policy decisions by end users.  CTB projects are carried out jointly by scientists from NCEP, other NOAA organizations and the broader research community. While the CTB facility is currently located at the NOAA Science Center in Camp Springs, MD, it will be moving to the University of Maryland’s M-Square campus in College Park in early 2008. This presents the CTB with tremendous opportunities in the near future.

1.1 Vision and Mission

The CTB strategy centers around its Vision and Mission.

What is the CTB Vision?

To significantly increase the accuracy, reliability, and scope of NOAA’s suite of operational climate forecast products to meet the needs of a diverse user community.

The notions of accuracy, reliability, and scope of climate forecast products correspond to CTBs 4 programmatic priorities (discussed in section 1.4) related to improving the NOAA Climate Forecast System, carrying out reanalysis and providing new and improved climate forecast products for decision making. The multi-model system used to produce forecast products will be based on a community model approach. Since the component models of the atmosphere, the oceans, land surface, hydrologic cycle, and biogeochemical cycles are at greatly varying stages of maturity, hierarchies of less detailed models and statistical models must also be employed.  All of these activities are aimed at the fundamental goal of enhancing our collective interdisciplinary ability to understand and predict the state and evolution of the Earth system.

What is the CTB Mission?

To accelerate the transition of scientific advances from the climate research community to improved NOAA climate forecast products and services.

1.2 Relationship to NOAA Strategic Plan

How is the CTB Vision related to the NOAA Strategic Plan?

The NOAA Strategic Plan “New Priorities for the 21st Century” (see http://www.spo.noaa.gov/pdfs/NOAA%20Strategic%20Plan.pdf ) is centered upon 4 Goals and a Support Goal:

- Protect, restore, and manage the use of coastal and ocean resources through an ecosystem approach to management;

- Understand climate variability and change to enhance society’s ability to plan and respond;

- Serve society’s needs for weather and water information;

- Support the nation’s commerce with information for safe, efficient, and environmentally sound transportation;

- Provide critical support for NOAA’s mission.

These strategic goals are frequently referred to as Ecosystems, Climate, Weather and Water, Commerce and Transportation, and Mission Support.

The CTB Vision speaks most directly to NOAA’s Climate Goal, but also to the Weather and Water, Ecosystems and Commerce Goals, and is closely aligned with the Support Goal.  The NOAA Strategic Plan also lists 5 essential activities that it refers to as “crosscutting priorities”.  The CTB Vision contributes directly to two of these: “Ensuring sound, state-of-the-art research”, and “Integrating global observations and data management”.  Finally, the plan also discusses outcomes, performance measures, strategies and activities associated with each Goal.  CTB outcomes and performance measures are discussed in Part I, Section 5.  The CTB programmatic and science priorities and implementation strategy are discussed below.

The CTB Vision also aligns with NOAA’s Five-Year Research Plan focus on Earth system modeling (to link weather & climate, oceans & land, biochemical processes, regional ecosystem models, etc.) and the associated observing systems and networks to support Earth system modeling (especially the Global Earth Observing System of Systems or GEOSS)

How are the CTB Vision and Mission aligned with the NOAA Climate Goal Programs?

The NCEP / CTB Vision and Mission are closely aligned with the mission requirements, capabilities, strategy and desired end states of the NOAA Climate Program (Fig. 1), and especially the desired end state of the Climate Predictions and Projections Program to provide “A Seamless Suite of Forecasts” (Fig. 2) on intraseasonal, interannual, and multi-decadal timescales and applications using ensembles of multiple climate models in support of the mission outcome “a predictive understanding  of the global climate system.”

The CTB Vision and Mission also align with the ten year NOAA Modeling Vision to embrace a unified Earth System Modeling Framework (ESMF) that maintains the U.S. as a recognized world leader in global Earth system modeling and meets the NOAA mission within the state of the science to meet customer requirements.

The CTB will embrace Earth system modeling used to analyze and predict the state of the atmosphere, the oceans, land surface, hydrologic cycle, and biogeochemical cycles within the framework of a unified multi-model system.  This implies an increasing alignment with other components of the NOAA Climate Program such as the the Climate and Ecosystems Program to “Understand and predict the consequences of climate variability and change on marine ecosystems.”

The CTB programmatic priorities (Part I, Section 1.5) include an ongoing analysis of the climate system that contributes directly to the Observations and Analysis Program to “Describe and understand the state of the climate system through integrated observation, analysis, and data stewardship.  Finally, the CTB programmatic priorities also include applications of climate forecast products that contribute to the Regional Decision Support Program to “Increase availability of climate forecast products and services to enhance decision making.”

Figure 1.  NOAA Climate Program strategy.

Figure 2.  NOAA/NCEP Seamless Suite of Forecast Products.

1.3 Objectives

To accomplish its mission, the CTB will accelerate the transition of scientific advances from the climate research community to improved NOAA climate products and services.  CTB objectives are

- to accelerate the synthesis and implementation of advances in climate model improvements, multi-model techniques, forecaster tools, data sets, and observing systems into NOAA climate forecast operations;

- to provide the climate research community with access to operational models, forecast tools and data sets to enable collaborative research that accelerates additional improvements of NOAA climate forecast products;

- to develop new and improved operational climate forecast products for the applications community to use in planning and decision making.

# 1.4 Requirements to Improve Climate Prediction

NOAA/NCEP is the lead for providing operational climate prediction on time scales ranging from weeks to years.  These predictions are aimed at enhancing our collective ability to understand and predict the state and evolution of the climate system, including linkages between climate and weather (including weather extremes) on all time scales.  Weather and climate extremes impact lives, property and the economy at levels which are many times larger than the investments needed for improving climate prediction.

Improvements in Intraseasonal-to-Interannual (ISI) prediction depend on a balance of new and existing resources dedicated to a few specific priorities (discussed below).   Accelerating improvements in ISI predictions requires a simultaneous attack from both short-term weather and long-term climate models and their modeling research strategies.  The limited skill of both approaches must be integrated with other forecasting tools using a multi-model ensemble approach, to integrate all possible known sources of independent forecast skill.  Numerical weather prediction models must be extended to climate time scales, and general circulation models being developed for climate change projections must produce skillful simulations at S-I time scales.

To achieve these objectives, the CTB will acquire the capability to run and support, for external users, the operational coupled Climate Forecast System (CFS) and other Earth system models within the framework of a multi-model ensemble system, to support other climate model components and to provide the public, including the CTB, access to experimental data and model components.

Some details on NOAA/NCEP requirements for improved climate prediction:

Multi-Model Ensemble Prediction System:  Studies by Krishnamurti et al. (1999), Palmer et al. (2004), and others have shown that the forecast skill of a multi-model system is higher than that of all of the individual models.  As a consequence, the international scientific community has rallied around the multi-model ensemble approach to improve climate prediction.   Several multi-model ensemble programs are underway around the world, notably those at EU (Provost / Demeter / Ensembles) and at the APEC Climate Center in Korea.  To maintain its status as a world leader in global Earth system modeling, NOAA should develop a systematic multi-model based prediction and projection capability and infrastructure.  The NOAA/CTB is a natural lead to develop the strategy.  Such a capability will allow focused research on phenomena that have been demonstrated by predictability studies to have the greatest potential to improve forecast skill on ISI time scales.  Increased availability of improved fully coupled models, access to data sets from multi-model experiments, and experimental prediction activities will result in new capabilities for the research community at large to contribute to predictability studies and an understanding of climate variability and change based on intercomparisons of model and observational data sets.  This capability includes an improved dynamical understanding of trends that are the physical basis for operational seasonal forecasts when ENSO is absent.

Though the fraction of the total variability of the coupled atmosphere-ocean-land-cryosphere system that is concentrated at ISI timescales is a small fraction of the total variability, the theoretical predictability limits are not currently realized in operational climate forecasts.  Improvements to operational climate forecast products are possible in the near term by employing calibration and consolidation techniques to combine statistical and dynamical forecast tools in a way that takes advantage of the independent skill that each tool brings to the climate forecast.

There is an increasing need to provide skillful climate change projections that can support policy decisions on air quality, ecosystem impacts, water-related issues, climate variability, and abrupt climate change.  By FY12 NOAA needs an Earth system model that provides an increased range of climate products for regional applications and decision support using these projections.  The future vision is centered around a capability to produce a seamless suite of products that span operational climate predictions, based substantially on output from multi model ensembles with significant utilization of Earth system models, and extending to a suite of new forecast products of impacts on the environment and ecosystems with quantification of skill level at global and regional scales.

Climate Forecast System (CFS) Improvements:   The CFS (Saha et al. 2006) is the first  NOAA 1-tier fully coupled atmosphere-ocean-land surface forecast system for ISI climate prediction to show skill at least equal to that of statistical seasonal prediction tools.  It is now clear that, having achieved at least parity with statistical algorithms, coupled numerical forecast systems have the greatest potential for improving climate forecasts beyond day 7.  Considerable scientific investigation and development is needed to accelerate improvements in the skill of these forecasts on ISI time scales.  The CTB facility provides additional infrastructure to help accelerate improvements in the CFS by bringing in the climate community to accelerate improvements and carry out the requisite transition to operations.  Unique resources for the “home research institution”, the CTB, and NCEP Central Operations (NCO) are required to carry out the code conversions, model calibration, skill assessments, parallel testing and operational implementation required for smooth transitions (see Appendix A).  The CFS contributes a significant portion of the current skill in predicting phases of the ENSO phenomena and their resultant impact on United States and global weather and climate.

Climate Forecast Products:  The overall objective is to increase the number and applicability of NOAA climate forecast products for use in decision making. Key challenges for the CTB are to identify what useful climate predictions can be made on ISI timescales; to determine the current accuracy of climate forecasts; to ask what needs to be done to improve / start useful operational predictions; and to identify how the predictions can be shared with potential users.  Success demands clear stakeholder benefits.

Common customer requests for improvements to NCEP/CPC climate forecast products include making products more easily understood, expanding beyond averages to extremes, giving more temporal and spatial detail and providing real-time access to models and data.  The CTB will endeavor to improve and strengthen basic predictand products, including conversion of monitoring and forecast products to GIS format with value-added information for application to local needs.  In addition, the CTB will provide enhanced verification statistics for official climate forecast products and tools.  Potential new products, such as the risk of high-impact weather events in a month or season by ENSO phase, will also be considered.

NCEP / CTB will provide significant contributions to the National Integrated Drought Information System (NIDIS), including new drought monitoring products that highlight hydrologic conditions (current,  week1, week2, monthly, seasonal) , new drought forecast tools, and real-time support for the operational drought monitor and drought outlook and the NIDIS portal.

The CTB will partner with intermediaries (e.g. NWS Climate Services Division; Regional Integrated Science and Assessments) to ensure that product improvements meet user needs.  It behooves NOAA to encourage and facilitate faster improvement of NOAA climate forecast systems, and at the same time to increase the exposure of NOAA climate forecast products linked to application models that extend the utility and scope of NOAA climate services.

Climate Reanalysis – An Ongoing Analysis of the Climate System (OACS):  NOAA Climate Program has requested the lead on developing new climate reanalysis data sets and to deliver explanations for the causes of observed climate variability and change. This effort is a key NOAA contribution to the CCSP goal of improving knowledge of the Earth’s past and present climate and environment, including its natural variability, and to improve understanding of the causes of observed variability and change (US CCSP, 2003). This work will enable NOAA to deliver a high priority interagency CCSP synthesis product: “Reanalyses of historical climate data for key atmospheric features. Implications for attribution of causes of observed change.” This program component supports NOAA’s Mission Goal to “Understand climate variability and change to enhance society’s ability to plan and respond”.

NOAA lacks adequate capacity to provide global climate analyses that are required to describe major features of 20th-century climate and the capacity to address the causes of observed regional climate variations that are crucial to informing policy decisions. The first-generation reanalyses, based on mid-1990s models and data assimilation systems, lack adequate spatial resolution and contain known deficiencies which limit their usefulness for identifying climate trends and assessing causes of observed change.  Advances in models, improved climate data assimilation methods, and new data sources make it desirable and feasible for NOAA to develop and continually update global reanalyses datasets. An assessment of the causes of observed changes will complement the data set development and enable NOAA to meet CCSP synthesis product requirements.

The benefits of an ongoing program include: (i) new quality controlled data products for use in the next generation reanalyses; (ii) production and dissemination of improved climate reanalysis data products for assessing climate variability and change; (iii) long term consistent reanalyses for initializing and verifying model hindcasts - a critical exercise for calibrating model forecasts; (iv) fulfillment of NOAA’s commitment to the CCSP goals; (v) new diagnostic tools to link the behavior of climate and forcing mechanisms in a physically consistent manner; (vi) regular and systematic explanations of past, current, and evolving climate conditions, and (vii) enhanced climate prediction capabilities that enable regional and national decision makers and resource managers to better plan for impacts of climate extremes, variability, and change.  Developing improved climate reanalyses and attribution capabilities requires strong links among NOAA’s observational, research, and operational prediction efforts. CTB can play a vital organizational role by coordinating ongoing reanalysis activities within NOAA, across agencies and internationally in order to determine the“best way(s)” to carry out historical reanalysis.

1.5 Programmatic and Science Priorities

The four component efforts identified as NOAA/NCEP requirements for improved climate prediction (Part I, Section 1.4) are referred to as CTB Programmatic Priorities.  Each of them is required as part of a balanced approach to improve ISI climate forecasts, products and applications.  If any component is not funded, or funded entirely to the detriment of the others, the loss of the non-supported component(s) will cause the entire interdependent system to fail.  The CTB is not (and cannot be) active in all of these areas: priorities will be developed and continue to evolve over time as outlined in the implementation strategy (see Part I, Section 2) for each of the programmatic themes.

2. IMPLEMENTATION STRATEGY

The CTB Programmatic and Science Priorities are the basis of the CTB Science Plan and Implementation Strategy (SP&IS).  The CTB Transition Project Teams (Part I, Section 2.1) are responsible for devising the strategy and carrying out activities designed to accelerate progress on these priorities.

2.1 Transition Project Teams

The CTB Transition Project Teams (TPTs) are the functional core of the CTB (see Appendix C for TPT Terms of Reference).  They are responsible for carrying out and analyzing CTB experiments and for enhancing collaboration between CTB staff, external PIs and the user community.  The TPTs have fostered many new joint activities between NCEP and the broader community that would not have occurred without them.

Currently there are 3 TPTs with several subgroups that have been organized for 3 of the 4 CTB Programmatic Priorities:

1.0 The Multi Model Ensemble Prediction System Team (Chair: Saha)
1.1  International MME Group (Saha)

1.2 National MME Group (Saha)

1.3 Consolidation Group (van den Dool)
1.4 Verification Group (Kumar)

2.0 Climate Forecast System Test & Assessment Team (Co-chairs:Moorthi & Schemm)

2.1 Experiment Group (Moorthi)
2.2 Assessment Group (Schemm)
2.3 Ocean Data Assimilation Group (Behringer)
2.4 Land Data Assimilation Group (Mitchell)

3.0 Climate Forecast Products Team (Chair: O’Lenic)
3.1 Climate Forecast Products Group (O’Lenic)
3.2 Drought Group (Mo)

In the future a TPT focused on Reanalysis may be organized if resources become available.

TPT membership includes CTB staff (federal employees and contractors), external PIs, focal points and members of the user community.  The bulk of the CTB science staff participates on one or more of the TPT groups.  Each TPT has a chair or co-chairs, who has (have) been appointed to lead the team and to report progress to the CTB Management and the CTB Climate Science Team (CST).  CTB PIs are encouraged to join a TPT in order to ensure that their activities are given sufficient computing resources.  The TPTs reflect the balance of internal and competitive projects at any given time.

How TPT projects are selected, ranked and completed:

On an annual basis, each TPT chair is asked to prepare a team-wide list of activities, including proposed experiments, with scientific justification, computational requirements, & anticipated impact on operations.  The TPT chairs ensure that all projects are included.

The CST collects this information and uses teleconferences and e-mail correspondence to prioritize TPT experiments based on relevance to CTB objectives and availability of CTB computer resources.  The CST ensures that competing requirements (e.g. increased model complexity and/or resolution and/or ensemble size) are properly weighed (see Appendix C for CST Terms of Reference) .  The above process is carried out each fiscal year after new CTB competitive projects are funded. The CST co-chairs work with the TPT chairs to ensure that experiments are completed.

TPT chairs are also required to provide an Annual Progress Report to the CST Co-Chairs (usually in late spring or summer) that summarizes progress on experiments, computer usage, and expected impact on climate forecast operations.  This information is reported by the CST co-chairs at the Annual SAB Meeting and reviewed by the SAB.

2.2 Strategy and Current Activities

A brief summary of the strategy and current activities for each TPT follows:

1.0 The Multi Model Ensemble Prediction System Team (Chair: Saha)

Strategy: Develop a MME Prediction System at NCEP with CFS included by doing the following:

- Establish collaboration with international operational centers that have required hindcasts (UKMO, Meteo-France, ECMWF, BMRC, BCC) for an International Multi-Model Ensemble (IMME);

- Establish collaboration with national centers (GFDL, NASA, NCAR) for a National Multi-Model Ensemble (NMME);

- Preliminary skill evaluation of IMME and NMME members;

- Consolidate the NMME and IMME into a single operational MME Prediction System;

- Workshop on scientific aspects of MME and lessons learned;

- “White Paper” vetted with SAB, OB and broader community.

See the “White Paper” entitled “Multi-Model Ensembles: Transition from Research to Operations and Implementation Strategy” for details on current activities, future plans, milestones, etc.

Group Activities:

1.1 International MME Group (Saha)

1.1.1 Preliminary skill evaluation of an IMME consisting of CFS and DEM3

(UKMO, Meteo-France and ECMWF) over Europe and US (VandenDool (CTB), Saha (EMC), Lord (EMC), Doblas-Reyes, Bougeault (ECMWF);

1.1.2 Preliminary skill evaluation of an IMME consisting of CFS + BCC over

China and US (Saha, Wang (CTB), Zhang (BCC);

1.1.3 Preliminary skill evaluation of an IMME consisting of CFS + BMRC over

Australia and US (Saha (CTB), Alves (BMRC));

1.2 National MME Group (Saha)

1.2.1 Preliminary evaluation of GFDL CM 2.1 hindcasts (1979-2006) for 4 initial months for their skill for ISI prediction (Saha (EMC), Thiaw (CTB), Gross (GFDL));

1.2.2 Port GFDL code to NCEP for timing & reproducibility testing (Saha (EMC), Thiaw (CTB));

1.2.3 evaluation of GFDL CM 2.1 hindcasts (1979-2006) for 8 remaining months for their skill for ISI prediction;

1.2.4 Add GFDL Model to the NMME (NCEP, GFDL) for subseasonal, seasonal and experimental forecast products;

1.2.5 Follow similar procedure for evaluating additional skill above CFS and GFDL for the NASA Model to the NMME (NCEP, GFDL, NASA) for subseasonal, seasonal and experimental forecast products;

1.2.6 Follow similar procedure for evaluating additional skill above CFS, GFDL and NASA for the NCAR Model to the NMME (NCEP, GFDL, NASA, NCAR) for subseasonal, seasonal and experimental forecast products;

1.3 Consolidation Group (van den Dool)

1.3.1 Comparisons of simple linear combination algorithms to weighted

combinations:

1.3.1.1 Seasonal-to-interannual Prediction (Van den Dool (CTB), Unger

(CTB)

1.3.1.2 Intraseasonal Prediction (Peng (CTB))

1.3.2 Incorporate the MME into the CPC consolidation scheme together with operational statistical tools;

1.3.3 Transition the MME Prediction System to NCEP Central Operations.

1.4 Verification Group (Kumar)

1.4.1 Submit CFS verification results to the WMO Lead Center for "Long-range Forecast" Verification (Kumar, Peng)

2.0 Climate Forecast System Test and Assessment Team (Co-chairs: Moorthi and Schemm)

Strategy: The CFS Test and Assessment (CFSTA) Team performs sensitivity experiments of various components of CFS and evaluates the results of those experiments.  The experiments are designed to accelerate assessment and development plans for CFS (ocean model and assimilation; land surface model and assimilation; physics; resolution) and to diagnose the biases in CFS/GFS and develop strategies to reduce them.  Experiments are proposed by the members of the team, and reviewed and ranked by the CST.  The investigators associated with the approved proposals to run on the CTB computer provide the CTB management brief status reports on a quarterly basis. After the proposed experiments are completed, the investigators provide a summary of their results to the CTB as well as the Climate Modeling Team of EMC so that these results can be used to guide the future development of CFS.  For FY 2008 and 2009, CFSTA Team will work closely with the EMC Climate Modeling Team and the CPC staff to evaluate and diagnose the new CFS suite projected for operational implementation in 2010.  The proposed time-line for the next CFS implementation in January 2010 is given in Appendix D; this timeline is subject to change.

Group Activities

2.1 Experiment Group (Moorthi)

CDEP Funded Projects to improve CFS (2nd year)

2.1.1 Using Initial Tend. Errors to Reduce Systematic Errors (PI: Delsole, COLA; Pan, Thiaw-NCEP)

2.1.2 Neural Network Emulations of Model Physics for CFS (PI: Fox, UMD; Kransapolsky, Hou, Saha-NCEP)

CST FY07 Internal Experiments

2.1.3 Old PBL CFS run to assess impact on ENSO (5 units) - (Jongil Han, Hua-Lu Pan and Suru Saha)

2.1.4 Hurricanes 4 warm seasons – T382L64 (9 units) – (Cathy Thiaw, Hua-Lu Pan and Suru Saha)

2.1.5 "QBO and vertical resolution – T126L100 and 150, 60 years each (30 units)" (Cathy Thiaw, Suru Saha and Mark Iredell)

2.1.6 "Radiation (spec res, trace gas, NN control) 30 years (1.5 units)" – (Yu-Tai Hou and Suru Saha)

2.1.7 "Higher res ocean (MOM4), changes in CO2 and solar cycle, (20 units)"- (Sudhir Nadiga, David Behringer and Jiande Wang)

2.1.8 "Subseasonal hindcsts at diff resolutions (T126, T254, T382), (289 units)" – (Augustin Vintzileos and Hua-Lu Pan)

2.1.9 Different trace gas elements (13 units) – (Sarah Lu and Yu-Tai Hou)

2.1.10 Fire danger Scripps (GFS/RCM+ocean) 23 yrs 10 member ens (46 units) –

(Henry Juang and Jun Wang)

2.1.11 Convectively-driven GWD in CFS – (10 units) – (Åke Johansson and Mark

Iredell)

2.2 CFS Assessment Group (Schemm)

CST FY07 Internal Experiments

2.2.1 Impact of warm bias east Pac (GFS with imposed SST) – 1 Unit – (Wang, Xie)

2.2.2 "NAMAP2 – impact of coupling, land initialization – 2.5 units" – (Mo, Schemm)

2.2.3Strat climate forcing (impact of new lw and ozone fcst code) – 1.5 units – (Long)

2.2.4 Offline Noah model (1948-2006) – improved forcing/bug fixes – 2 units – (van den Dool, Fan)

2.3 LDAS Group (Mitchell)

CST FY07 Internal Experiments

2.3.1 LDAS – repeat 27 year reanalysis with new attributes in (1 unit) – (Mitchell)

2.3.2 Impact of Noah LSM and land initialization (from above) in CFS (8 units) – (Mitchell)

2.4 ODAS Group (Behringer)

CDEP Funded Projects to improve CFS (2nd year)

2.4.1Ocean Component of the NCEP ENSO CFS (PI: McPhaden, PMEL; Xue-NCEP) - CTB;

CST FY07 Internal Experiments

2.4.2 GODAS – new multivariate scheme (correct surface winds) (1 unit) –

(Behringer)

2.4.3 GODAS - CFS reruns 1981-89 –impact of GODAS errors (25 Units) –( Yan Xue, Wanqiu Wang and Peitao Peng)

3.0 Climate Forecast Products Team (O’Lenic)

Strategy: Develop new and improved climate forecast and analysis products that enhance decision making.  Key objectives are to:

- Develop enhanced monitoring, assessment and prediction products and applications for the National Integrated Drought Information System (NIDIS);

- Convert CPC official monitoring and forecast products to GIS format;

- Facilitate interactions between CPC and the user community (RISAs, ARCs, etc.)

- Develop plans for Climate Reanalysis – An Ongoing Analysis of the Climate System (OACS) -

3.1 Climate Forecast Products Group (O’Lenic)

CDEP Funded Projects to Support Climate Forecast Product Improvements (FY07)

3.1.1 Probabilistic forecasts of Extreme Events and Weather Hazards in the US (PI: Charles Jones (UCSB); NCEP Co-PI: Jon Gottschalck (CTB))

3.1.2 System-wide Advancement of User-Centric Climate Forecast Products (PI: Holly Hartmann (UAZ); NCEP Co-PI: Ed O’lenic (CPC))

3.2 Drought Group (Mo)

CPPA Funded Projects to Support NIDIS

3.2.1 K. Mitchell (EMC) and J. Schaake -  (GAPP Core Project) -Seasonal forecast component to NLDAS; Retroactive NLDAS; Multi hydrology models (Noah, SAC, VIC, Mosaic) framework; Improved land model (snow, dynamic vegetation)

3.2.2 Dennis Lettenmaier (UW) “West-Wide” Hydrologic Prediction System -Monitoring and seasonal prediction; Bias correction of forcing

3.2.3 Eric Wood (Princeton) “East-Wide” Hydrologic Prediction System - Monitoring and seasonal prediction; Bayesian techniques to blend dynamical and empirical predictions

3.2.4 Brian Cosgrove (NASA/GSFC): - 27-year retrospective NLDAS forcing derived from RR;

3.2.5 Kingtse Mo (CPC) -New drought monitoring indices; Drought monitoring with RR and NLDAS

3.2.6 Van den Dool (CPC) - Leaky bucket soil moisture model which is used in current Drought Monitor

3.0  SCIENTIFIC PARTNERSHIPS

To be successful, the CTB will emphasize partnerships with the research and applications communities.  Both the internal (NOAA) and external research communities must be involved through bi-directional flow of climate information and opportunities to influence the CTB.  The CTB must engage the applications community to identify and meet demands for new and improved climate forecast products.  It is essential that the stakeholder community be engaged and permitted to develop a sense of ownership of CTB.  In addition, the private sector and the international research community have a lot to offer the CTB by way of partnerships and information gathering and sharing.  The CTB will endeavor to enhance these relationships, for example by broadening SAB membership to include these communities.  We will ask for community advice through service on our boards and panels, but recognize that there is an expectation of funding opportunities.

Some specific examples of activities that will strengthen CTB partnerships with the community include:

          - NCEP Move to the University of Maryland

In early 2008 the CTB facility will be moving along with NCEP to the University of Maryland’s M-Square campus in College Park, MD.   In addition to the NOAA Center, a second building immediately adjacent to the NOAA building will house the Earth System Science Interdisciplinary Center (ESSIC), the Cooperative Institute for Climate Studies (CICS), the DOE Joint Global Change Research Institute, personnel from the NASA/Goddard Modeling and Assimilation Office, and possibly others.  As stated in a recent white paper, this combination of climate researchers will establish the M-Square campus as a “National Center of Excellence for Environmental Research, Education, Applications and Operations”.  The CTB welcomes this opportunity to work closely with this world class team of scientists.

          - CTB Interactions with RISA’s and ARC’s

An NCEP/CTB – RISA Partnership Program was established during FY06 to identify and meet user needs for enhanced climate forecast products and applications.  To date CTB has engaged several of the RISA’s:

RISA			CPC/CTB Liaison	RISA Contact

SECC 			Muthuvel Chelliah 	James Jones / Jim O’Brien

PEAC / PaCIS		Luke He 		Jim Weyman / Eileen Shea

Alaska 		Jon Gottschalck	Lisa Vaughn / James Partain

CAP	 		Kingtse Mo		Dan Cayan / Mike Dettinger

CLIMAS		Ed O’lenic		Holly Hartmann

WWA			Michelle L’Heureux	Andrea Ray

The partnership program exchange visits work as follows:

(i) CTB/CPC makes short visits to the RISAs (or ARCs) to provide customized CPC overviews of our forecast, monitoring and assessment products. 
(ii) The RISAs (ARCs) send longer term visitors (up to several months) to CPC to develop customized products off of the CPC product suite.

          - Relationships to other NOAA Centers and Testbeds

It is important that the CTB Management work closely with other test beds and advocate projects that may have a direct bearing on the climate forecast problem.  The NASA-NOAA-DOD Joint Center for Satellite Data Assimilation (JCSDA) has considerable expertise and infrastructure in several areas of interest to the CTB, including atmosphere, ocean, land surface data assimilation, and the use of satellite data in support of climate applications, reanalysis, and the global observing system. The Joint Hurricane Test Bed is expected to coordinate its activities with those of other NOAA centers such as the NOAA Labs and Cooperative Institutes, NCAR and NASA.

The NOAA Hydrometeorology Testbed (HTB) will accelerate the implementation of operational hydrometeorological products and services, including enhancing and extending forecast skill for high-impact weather, especially precipitation, by facilitating interactions among researchers and operational forecasters.  The CTB will collaborate with the HTB in several areas, especially improved warm season precipitation forecasts, use of ensemble model output and forecaster generation of probabilistic products, and improved operational monitoring and prediction of weather–climate linkages.  With advancements in land surface modeling and land data assimilation techniques, the hydrometeorological community has also made considerable progress in streamflow prediction, drought monitoring, and anticipating extreme events. The CTB will endeavor to use the CFS forecasts to enhance hydrometeorological applications.

          - National and International Climate Programs

The CTB has strong linkages to several national and international programs including CLIVAR and GEWEX, and joint CLIVAR-GEWEX Programs, including the Variability of the American Monsoons (VAMOS) Program, the North American Monsoon Experiment (NAME), Monsoon Experiment South America (MESA), VAMOS Ocean Cloud Atmosphere Land Study (VOCALS), and the Coordinated Enhanced Observing Period (CEOP).  Linkages with these and other programs are expected to continue to intensify as the CTB ramps up over the next several years.

The CTB is closely related in concept to the CLIVAR Climate Process and modeling Teams (CPTs), which bring observationalists together with climate and process modelers to focus on key problems in climate models. The CTB priority of accelerating improvements in NOAA climate forecast models and reducing biases in NOAA climate model simulations and forecasts can be considered as the NOAA implementation of the CPT concept.  Linkages to existing CPT-like efforts at NCEP (e.g. the NAME CPT; the GAPP Core Project CPT for land) are likely to be enhanced in the future.

CTB Personnel are also members of various CLIVAR and GEWEX Panels, both in the US and internationally, including the US CLIVAR Predictions Predictability and Applications Interface (PPAI) Panel, the Climate Prediction Program for the Americas (CPPA) Science Panel, and the international CLIVAR VAMOS Panel.

The CTB welcomes the convergence of weather and climate research and forecasting activities proposed by THORPEX.  These activities will accelerate NCEP’s ability to deliver products that link weather and climate information using NCEP weather and climate models and other Earth system models within the framework of a multi-model ensemble prediction system.  These products will help meet demands for new and improved regional and sectoral applications of weather and climate forecast products that enhance decision making.

          - Earth System Modeling Framework (ESMF)

NOAA is migrating to a software framework provided by the Earth System Modeling Framework (ESMF).  ESMF is a structured collection of software building blocks that can be used or customized to develop Earth system model components, and assemble them into applications. The simplest view of the ESMF is that it consists of an infrastructure of utilities and data structures for creating model components, and a superstructure for coupling them. In order to be consistent and relevant to NOAA’s future software framework, which will itself accelerate the ability to support a multi-model ensemble forecast capability, the CTB will support CFS components within the ESMF and promote the introduction of other system components, for example as it develops a multi-model ensemble prediction system.

4.0 TECHNOLOGY TRANSFER

NCEP is uniquely positioned to provide an operational infrastructure for the model transition process.  EMC and NCO have critical roles in the transition from NOAA R&D to operations (Fig. 3), while CPC is one of several service centers that deliver products to users.  Defining responsibilities and providing resources for host research institutions, NCEP, and the applications community are required to ensure smooth transitions.  A fundamental role of the CTB is to identify and delineate the different types of transition (Part I, Section 4.1) whose guidelines must be systematic (Part I, Section 4.2).  The transition process also requires a comprehensive data policy for NCEP climate data sets (Part I, Section 4.3) to enhance collaboration and joint projects between internal and external participants on the CTB.  The CTB relies on traditional formal and semi-formal scientific vehicles for communicating interim and final results (Part I, Section 4.4).

Figure 3.  NCEP’s role in the model transition process.

4.1 Types of Transition

There is a large “volume” of funded research and development work, but only a small fraction of this is suitable for transition to operations.  Systematic transition steps are required to develop and deliver skill-optimized forecast products to a diverse user community and to ensure that user feedback is incorporated.  Thus, an important role of the CTB in the transition process is to clearly identify and communicate the scope of responsibilities for the climate research community, the NOAA operational centers, and the applications community.  In particular it is necessary to clearly distinguish the different types of transition:

Research to Operations: define where the operational center picks up

responsibility, and at what juncture a "hand-off" from the research

community occurs (see Appendix A).

Operations to Applications: define where the applications community picks up

responsibility, and at what juncture  a “hand-off” from the operations

community occurs (see Appendix B).

Research to Applications: define where the applications community picks up

responsibility, and at what juncture  a “hand-off” from the research

community occurs.

The CTB facilitates these transitions for the operational climate forecast product range (6-10 day, week 2, monthly and seasonal).  It is important to recognize that transitions work in both directions.  The transition of research to the applications community, and user feedback proceeds via the R2O, O2A and R2A transition steps.

4.2  Transition Guidelines

The CTB has established “Research to Operations (R2O) Guidelines” (see Appendix A) that specify the path to implementation of changes in the NCEP operational climate model suite.   Procedures for testing changes in parameterizations in the NCEP GFS/CFS are given at the end of Appendix B.   The CTB has also established some “Operations to Applications (O2A) Guidelines” that specify the steps for operational tools to be consolidated into the CPC seasonal forecasts and the steps for delivery of models, tools and datasets to a diverse user community (see Appendix B).  Collectively, these guidelines establish the roles and responsibilities of the host research institutions, the operational center, and the applications communities.

4.3 Data Policy and Access

The NCEP/CTB Climate Data Policy for access to operational and non-operational climate data sets is given in Part II, Section 4.4.  The policy applies to all climate data sets produced by NCEP.

Dissemination and archiving of CTB climate data sets is done through the NOAA Operational Model Archive and Distribution System (NOMADS).  GFDL and NCEP scientists have been part of a larger consortium that has been developing NOMADS capabilities for broad data set availability.  One of the CTBs early successes has been to provide a complete CFS hindcast data set, including daily resolution for selected fields and monthly means for the entire set of variables and levels.  In the future the CTB will avail itself of other avenues for providing online access. There needs to be an open process for determining when and how best to share data from CTB activities, including the nature of the data sets to be shared (output frequency, variables, etc.), the requirement and allocation of resources for quality control of research data sets, and how data sets generated outside NCEP are to be handled.  The NCEP/CTB Data Policy for climate data sets will continue to be improved as part of this process.

4.4 Communicating Results

Results from CTB Transition Projects are disseminated in a number of ways.  During the initial stages, CTB scientists often present preliminary ideas and results at internal meetings with NCEP colleagues and TPT members.  The collocation of EMC, CPC and CTB at NCEP, as well as the collocation of NOAA, NASA, U Md  COLA, and GMU greatly facilitates these types of interactions.   The CTB also relies on traditional informal and semi-formal scientific vehicles for communicating interim and final scientific results with NOAA and the broader scientific community.  These include:

          - Seminars – CTB scientists are frequent participants in the regular NCEP CPC and EMC seminar series and in seminars elsewhere (e.g. COLA, CICS, ESSIC, etc).

          - Informal Publication – CTB personnel contribute to a wide range of scientific newsletters, such as CLIVAR Variations, the VAMOS Newsletter and GEWEX News.  Over the past 2 years the intention has been to inform the community about the CTB.  In the future we anticipate that this will be a vehicle for communicating immediate results (including availability of models and datasets) to the broad scientific community.

          - Reports – CTB reports on each of its projects on an annual basis by collecting information from the TPTs  and PIs.  Starting in FY07 the CTB Management will also provide Annual Reports that summarize important developments and research results during the preceding year.

          - Atlases – From time to time, the CTB produces compendiums of multi-year data sets (such as CFS hindcasts) that make intercomparisons and assessments of model improvements more convenient.

          - Formal Publications – CTB personnel place a high priority on publications in refereed journals.  A list of recent publications will be included in the next draft of the SP&IS.

          - Workshops – The CTB participates in the Annual Climate Diagnostics and Prediction Workshop, with several sessions dedicated to reporting the results of CTB science activities.  In addition, the CTB will continue to hold annual SAB meetings to discuss CTB progress and request advice on future science priorities.  In the future the CTB will hold annual PI meetings, either as stand alone meetings or in conjunction with other CPO programs.  Also, CTB personnel are increasing their participation in large annual meetings and topical workshops (e.g. CSD Climate Prediction Applications and Services (CPAS) Workshops, RISA PI meetings, etc.).

Although NOAA communicates its programmatic interests to the CTB in numerous ways (e.g. NOAA Strategic Plan, Annual Guidance Memorandum, Five Year Research Plan, 20 Year Research Vision, other planning documents created by NOAA line offices), the CTB continues to search for methods that enhance communication with NOAA scientific partners.  Annual “CPO-NCEP Dialogue meetings” (since 2004) have been effective vehicles for communicating priorities and developing strategies for improved ISI predictions.  The CTB Management seeks other avenues that enhance CTB awareness of NOAA and community wide research priorities.

5.0 PROGRESS ASSESSMENT

A number of criteria are used to measure progress in accomplishing CTB objectives.  Internal evaluation of CTB progress is done in two ways: through the annual evaluation of individual scientists by the CTB Director and through the periodic meetings of CTB Management, OB and SAB.  The assessment of success of individual scientists is based on completion of items in individual GWPS workplans that contribute to the CTB mission.  Contributions to CTB Projects and collaboration with the external community are important components.  In addition, the evaluation is based on other, more traditional measures, including publication of scientific results in peer-reviewed journals, and success in proposing research to operations tasks to NOAA and other funding institutions.

Though the CTB is new, the rapid increase in the number of CTB internal and competitive projects and CTB-related publications is indicative of the level of enthusiasm for the CTB concept as well as the increasing diversity and volume of our scientific work.

The Terms of Reference for the CTB OB are given in Appendix C.  One of their functions is to review and approve the research and development themes and priorities of the CTB.  CTB management prepares an Annual Report that summarizes CTB activities during the preceding fiscal year to facilitate this.

Another criterion used to measure CTB success is contributions to the NOAA mission. Key expected results from CTB transition projects are selected and defined based on their potential to contribute to NOAA Goals.  The links to the objectives include a set of discrete steps, or milestones, for achieving these improvements.

CTB milestones are tied to the Programmatic Priorities (Part I, Section 1.5).  The milestones are updated on an annual basis as part of the NCEP Annual Operating Plan (Part II, Section 5).  Progress on CTB milestones is reported each quarter to NCEP management.

5.1 Performance Objectives

The effectiveness of the CTB will be judged, in part, through its contributions to NOAA performance measures.  The CTB has adopted the following metric:

| Performance Goal: Climate | FY06 Baseline | FY07 | FY08* | FY09 | FY10 | FY11 | FY12 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Performance Measure with Adjustment % improvement over current GPRA targets (skill of US seasonal temperature forecasts) | 0 | 0 | 0 | 0 | 5% | 10% | 15%** |
| Performance Measure without Adjustment | 0 | 0 | 0 | 0 | 0% | 0% | 0% |

Here it is assumed that the lead time for implementation of developments and improvements is 2 years.  Heidke scores on the books and CTB improvements (starting in FY10) are: FY06 (18); FY07 (19); FY08 (19); FY09 (20); FY10 (21; 22); FY11(21;23); FY12 (22; 26).  Note that a 15% improvement over the FY12 GPRA target of 22 is a 40% improvement over the FY2006 baseline number of 18.

5.2 Expected Outcome

The CTB will contribute directly to the NOAA Goal to “Understand climate variability and change to enhance society’s ability to plan and respond”.   Specific CTB contributions to the desired end state will include:

- New and improved data sets and components for NOAA operational climate forecast systems;

- New and improved tools and methods to provide more skillful climate forecasts;

- Greater understanding of operational model strengths/weaknesses and biases via assessment and detailed analyses of model diagnostics;

- Enhanced use of climate observations for new and improved climate forecast products;

- New and improved climate forecast products for use in decision making;

- Evaluation and refined requirements for global observing systems.

6.0 REFERENCES

Krishnamurti, T. N., C. M. Kishtawal, T. E. LaRow, D. R. Bachiochi, Z. Zhang, C. E.

Williford, S. Gadgil, and S. Surendran, 1999: Improved weather and seasonal

climate forecasts from multi- model superensemble. Science, 285, 1548–1550.

Palmer, T. N., A. Alessandri, U. Andersen, P. Cantelaube, M. Davey, M. Déqué, E. Díaz,

F. J. Doblas-Reyes, H. Feddersen, R. Graham, S. Gualdi, J.-F. Guérémy,

R. Hagedorn, M. Hoshen, N. Keenlyside, M. Latif, A. Lazar, E. Maisonnave,

V. Marletto, A. P. Morse, B. Orfila, P. Rogel, J.-M. Terres and M. C. Thomson,

2004. Development of a European Multi-Model Ensemble System for Seasonal to

InterAnnual Prediction (DEMETER). Bull. Amer. Meteor. Soc., 85, 853-872.

Saha, S, S. Nadiga, C. Thiaw, J. Wang, W. Wang, Q. Zhang, H. M. van den Dool, H.-L.

Pan, S. Moorthi, D. Behringer, D. Stokes, M. Peña, S. Lord, G. White,

W. Ebisuzaki, P. Peng, P. Xie , 2006 : The NCEP Climate Forecast System.

J. Climate (in press)

USCCSP, 2003: Strategic Plan for the U.S. Climate Change Science Program.

Climate Change Science Program and Subcommittee on Global Change Research.

Climate Change Science Program Office, 1717 Pennsylvania Avenue, NW, Suite

250, Washington, DC 20006

PART II.  MANAGEMENT AND OPERATIONS PLAN

1.0 FRAMEWORK

The CTB framework consists of infrastructure, internal (NCEP Technical Operating Plan or NTOP) projects, and competitive (AO-driven) projects focused on key science priority areas (see Part I, section 1.4)   A balance among the categories that make up this framework is essential to ensure the overall success of the CTB.

1.1 Infrastructure

The CTB infrastructure includes computing resources, Management and Administrative Staff, Transition Project Teams (TPTs), System Support Team, and a Visiting Scientist program (detailed Terms of Reference are given in Appendix C).   CTB infrastructure will support the exchange of climate models and data with the external community.  Augmentation funding for the System Support Team is required to facilitate these exchanges.  The CTB infrastructure will support a capability for generating and producing multi-model ensembles (subject to the CTB transition guidelines given in Appendix A).  The CTB will support and maintain Earth System Modeling Framework (ESMF) compatible software for global coupled models participating on the CTB.  The CTB will support outreach, through the applications community, for the purpose of increasing the number and skill of climate forecast products for decision makers.

CTB computing support includes 1/3rd of the NOAA Research supercomputer cluster.  If one unit is the CPU time for a 10 year run of the fully coupled CFS run at a resolution of T126L64 (this is a higher resolution than the current operational model, which is run at T64L28), then this resource is equivalent to approximately 200 units or 200 / 10 year runs per Fiscal Year.

NCEP contributions to the CTB include redirected federal staff for CTB management and administration and for the Transition Project Teams (TPTs).  Since 2004 the CPO has provided augmentation funding for an additional system support staff person (to prepare and disseminate CFS hindcasts).

NCPO competitive research programs provide a venue for scientists in the external research community to work with CTB personnel on key science priorities detailed in Part I, Section 1.5 and Part I, Section 2.

While the bulk of the computing resources are supplied by NCEP, there is limited manpower to provide system support to the external community (e.g. to transfer models and data and to maintain computing infrastructure).  CTB relies on augmentation funding for this.  CTB transition projects are carried out by the TPTs, PIs participating in competitive research programs, and their NCEP sponsors.  Grants may support contractors and Visiting Scientists.  Terms of Reference for CTB teams and the Visiting Scientist Program are given in Appendix C.

1.2 Transition Projects

The scientific work in the CTB is accomplished via collaborative transition projects, which include both internal projects and competitive projects (funded via Announcements of Opportunity).

Internal projects will generally be short-term activities, with potential for direct impact on NOAA climate models, forecasts, and application products in 2 years or less; these projects constitute the CTB NTOPs (see Part II, section 5.1).  They are generally accomplished using FTEs reallocated from NCEP and other line offices.  These projects have definite outcomes and lifecycles.  They are selected by CTB management in consultation with NCEP senior management.

Competitive Projects are funded using annual Announcements of Opportunity (AOs).  These projects are generally long-term projects with potential for impact on NOAA climate models, forecasts and application products in 2 or more years.  CPO will undertake administrative tasks. These projects can include NOAA or external lead PIs.  The procedures to identify competitive transition projects are discussed in Part II, Section 4.  Proposal selection and peer review will be managed by CPO with input from CTB Management.  If other agencies contribute, their input is considered in the selection process.

1.3 Facility

The CTB facility is currently located at the NOAA Science Center in Camp Springs, MD.  The CTB has a dedicated physical space and computer facilities.  In early 2008 the CTB will be moving along with NCEP to the NOAA Center for Weather and Climate Prediction at the University of Maryland’s M-Square campus in College Park, MD.  At M-Square the CTB will also have dedicated physical space for CTB personnel, and computing facilities.   Whereas a core of researchers, contractors, visiting scientists and a small administrative staff will be housed at the CTB, other researchers and their associated contractors and focal points may be distributed both geographically and organizationally.

1.4 Organization

The CTB includes a Director, a Deputy Director for Administration, a Deputy Director for Transition to Operations, an Oversight Board (OB), a Program Manager, an Administrative Staff, a Climate Science Team (CST), Transition Project Teams (TPTs), a System Support Team, and a Visiting Scientist Program.  CTB Personnel include civil servants, contractors, visiting scientists and students.  An external Science Advisory Board (SAB) provides scientific advice and reviews CTB activities annually.   A schematic of the CTB organization and oversight and the Terms of Reference for CTB management, boards and teams are found in Appendix C.

2.0 STAFF

Since CTB is not formally an administrative element of NCEP, identification of CTB staff is subject to some ambiguity.  The CTB Director, Deputy Directors and Program Manager are considered to be CTB staff.  In addition, NCEP employees and contractors who work on CTB NTOPs (see Part II, Section 5.1) or who are supported by CTB grants are considered to be CTB staff.  Any students, visiting scientists, or non-NCEP employees who are supported by a CTB grant are also considered to be CTB staff.  External PIs who participate on the CTB, but who are not paid by their grants, are not considered to be CTB staff for counting purposes.

The Director, Dr. Wayne Higgins, Deputy Director for Administration, Dr. Mel Gelman, and Deputy Director for Transition to Operations, Hualu Pan are all half time CTB staff members (1.5 FTEs).  Currently, there is no CTB Administrative staff (this is an important issue).  In addition, there are at least 30 NCEP employees serving on the CTB TPTs (both federal and contract employees); many of the TPT members work part time on the CTB and part time on other NCEP tasks, so the number of personnel involved in CTB-related transition projects is larger than the total number of FTE’s.

3.0 FUNDING

The CTB has attracted new funding for transition projects via competitive research programs managed by the NOAA Climate Program Office (NCPO).  The funding profile for these projects since 2004 is as follows: $100K in FY04; $300K in FY05; $450K in FY06 and $650K in FY07.

4.0 COMPETITIVE TRANSITION PROJECTS

4.1 Initiation Procedure

CTB Programmatic and Science Priorities are identified using the procedures discussed in Part I, Section 1.5.  These priorities are provided to agencies participating in the CTB to be used as guidance in preparing Announcements of Opportunity (AOs) for competitive transition projects.  CTB AOs will also indicate how much computer time (total for all proposals) is available under that announcement, so that PIs will have an indication of what they can potentially request. CTB competitive (AO-driven) projects go through the normal merit review process.  This begins with the submission of a Letter of Intent to the Program Manager.

The Program Manager, in consultation with the CTB Science Management Team (Appendix C), identifies LOIs that fit CTB Science Priorities and contacts the PI to encourage or discourage a full proposal.  If a full proposal is encouraged, NCEP is committed to collaborate in the project should the full proposal be successful through the competitive merit review. For each encouraged LOI, the CTB Science Management Team will name an NCEP scientist as the point of contact (POC) to discuss with the PI on NCEP’s contribution and commitment to the prospective project, when developing the full proposal. If the resulting full proposal is recommended for support by the competitive merit review, the NCEP POC will work with the PI throughout the project and will be responsible for any necessary testing of the new techniques at NCEP in the operational environment.

The CTB Program Manager conducts the merit review process, and makes funding decisions in consultation with the CTB Management.  A “Computer Resource Request” must be submitted to the CST co-chairs at the time of proposal submission, to be taken into account as part of the proposal resource evaluation (see Part II, Section 4.2).  If a proposal is recommended for funding, and obtains the required CTB computer resources, then the proposal is funded.

4.2 Computer Resources Request

Final approval of a proposal depends on both the merit review and on the availability of computer resources (when required).  A “Computer Resource Request” must be submitted to the CST co-chairs at the time of proposal submission.  The required elements of the “Computer Resource Request” are:

- Name and contact information for PIs;

- The CTB Transition Project Team (TPT) and contact person at NCEP;

- A brief (200 words or less) description of the project;

- A brief (200 words or less) description of computer experiments;

- A justification for CTB computer resources;

- Specific computer time request (one unit=CPU time for a 10 year CFS (CMIP) run at T126L64; at present CTB has roughly 200 units per Fiscal Year)

Once a proposal has been selected based on merit (Part II, Section 4.1), the CST Co-Chairs convene a panel made up of non-conflicted members of the CST as well as independent scientists.  The panel determines the allocation of computer time based on available resources (but NOT based on a proposals scientific objectives).  The evaluation of CTB science objectives and priorities will have taken place as part of the merit review process (Part II, Section 4.1).

Panel recommendations are forwarded to the CTB Management (including CTB Program Manager(s) and the OB for final approval (generally no later than 1 November each Fiscal Year).  The CST Co-Chairs oversee progress of the TPTs, which carry out the experiments and provide Annual Reports to the CST and CTB Management.  CTB SAB meetings, Special Sessions (e.g. as part of the Climate Diagnostics and Prediction Workshop) and PI meetings (future) are used to report progress on TPT Experiments and CTB Projects (Part II, Section 5.4).

4.3 Computer Access

The computer resource request procedure (Part II, Section 4.2) is the basis for allocation of CTB computing resources for CTB projects.  The procedures meet with the approval of the OB and adhere to NCEP guidelines.  NCEP/NCO will provide management of the computing resources (user access, accounting, etc) according to established NCEP policies.  An NCEP Computing Oversight Board, consisting of the NCEP/NCO Director, the NOAA Environmental Modeling program manager, the NCEP/EMC Director, and the NCEP/CPC Director, enforces NCEP computing resource policies, including those of the CTB.

4.4 Data Policy and Access

The NCEP/CTB Climate Data Policy for access to operational and non-operational climate data sets is as follows:

- All climate data sets produced by NCEP on NCEP computers are public property;

- Climate data sets produced by NCEP Central Operations are available on operational servers and maintained 24/7;

- Climate data sets produced by EMC, CPC and CTB competitive transition projects will be made available on request, on non-operational servers during regular business hours (8/5);

- Requests for climate data sets should be in writing to CTB Management (Director or Deputy Director).  Once per month the CTB Management summarizes requests for climate data sets and seeks advice for filling requests from the individual Center Directors;

- EMC, CPC and CTB will make non-operational datasets available as quickly as possible, but users should expect a turnaround of 90 days or more depending on the availability of human and computer resources;

- If resources are an issue, and longer turn around time is necessary, the CTB will promptly inform the requester of any delays;

- Because storage for non-operational datasets is limited, each non-operational data set will be available for three months before it is removed;

- A list of CTB projects and investigators will be maintained by the CTB management;

- During the initial data analysis period (6 months after the data were produced), no data produced by CTB competitive transition projects will be provided to a third party (journal articles, presentations, research proposals, other investigators) without the consent of the investigator who produced the data. This initial analysis period is designed to provide an opportunity to adequately quality control the data set.

The CTB data policy applies to all climate information provided by CTB.

4.5 Conflicts of Interest

Conflict of interest is a very serious concern of the CTB.  The Terms of Reference for the CTB management and the various CTB boards and teams (Appendix C) are chosen to minimize potential conflicts of interest.

The CTB Management (Director, Deputy Directors and Program Manager) and CST co-chairs may not submit CTB proposals to competitive research programs.  However, the SAB and the OB may submit proposals and be selected as CTB investigators in free and open competition.  The SAB advises the OB, and the Directors of the NOAA Climate Office and NCEP on issues pertaining to CTB activities. This advice is more in the nature of broad policy or other guidance on science priorities as opposed to specific proposal reviews, or working level resource decisions (i.e. areas where conflicts most naturally arise). As with any other panel activity, where there are real or perceived conflicts on any specific issue, SAB members are asked to excuse themselves from discussions on that specific issue.  The same arguments hold for the OB.

Another conflict of interest issue pertains to the composition of the TPTs. Consistent with practices at NASA and other agencies, the TPTs consist of CTB members at NCEP, external PIs, contractors and users.  The TPT membership should reflect the balance of CTB base funded and AO-driven transition projects.

5.0 ANNUAL OPERATING PLAN

The CTB Annual Operating Plan (AOP) maps CTB infrastructure (human and computing resources) onto NCEP Technical Operating Plans (NTOPs).  Careful attention to the AOP, which is prepared early in the Fiscal Year, helps the CTB avoid duplication with other NCEP centers and makes maximum use of limited resources.

5.1 NTOPs

The NCEP Technical Operating Plans (NTOPs) are internal contributions to the CTB transition projects.  The components of the NTOPs include objectives, lead coordinator, relationships to the NOAA strategic plan, relationships to NCEP centers, and expected results.

During FY07 the CTB had 4 NTOPs:  (1) Climate Test Bed Directors Office; (2) Climate Model Improvements; (3) Multi Model Ensemble Prediction System, and (4) Climate Forecast Products.

5.2 Milestones

Expected Results in the CTB NTOPs  are selected and defined based on their potential to contribute to NOAA Goals.  The links to the Performance Goals should include a set of discrete steps, or milestones, for achieving these improvements.  The current set of CTB provisional milestones are linked to activities of each of the Transition Project Teams, and maintained by CTB management.  The CTB milestones are updated on an annual basis as part of the CTB AOP.   Progress on CTB milestones is reported each quarter to NCEP management.  In addition, annual progress on CTB milestones is included in the CTB Annual Report (Part II, Section 5.5), which is sent to the OB as well as the Directors of NCEP and NCPO.

5.3 Budget

The CTB prepares and oversees an annual budget as part of its Annual Operating Plan.   The annual budget maps resources onto expected results and related deliverables. Major components of the CTB budget are infrastructure (administration, system support, TPTs, visiting scientists), Announcements of Opportunity (AOs) and internally funded projects.

5.4 Meetings

Science Advisory Board (SAB) Meetings

SAB Meetings will be held at least once per year.  The purpose of these meetings is to gather independent expert advice on CTB progress and future science priorities.  CTB staff will review progress on Science Priorities, including implementation strategy, progress on current activities, future plans and milestones. Expected outcome includes a SAB written summary report, with recommendations to CTB Management and the OB.  CTB Management will provide a formal response to the SAB, and will use advice to update the SP&IS document and provide guidance to the agencies on future science priorities.

Special Sessions and PI Meetings

CTB Special Sessions with themes tied to ongoing Projects will be held in open meetings.  CTB has an established relationship with the Annual Climate Diagnostics and Prediction Workshop which is held each October.  CTB will expand its participation in large annual meetings (e.g. AMS Annual meeting) and topical workshops (e.g. Climate Prediction and Application Sciences (CPAS) workshops, RISA PI meetings).  As the number of competitive transition projects grows, the CTB may establish annual PI meetings, either as stand alone meetings, or in conjunction with another CPO competitive research program.

Management Team Meetings

The CTB Management Team (Director, Deputy Directors and Program Manager) holds routine monthly meetings to discuss CTB progress and plans.  Advice from the SAB, OB and the broader climate community is discussed at these meetings.  CTB personnel are encouraged to participate and to provide their ideas to the SAB, OB or Management Team at any time for consideration.

Teleconferences

The CST, SAB, OB and TPTs hold occasional teleconferences on focused topics.  PowerPoint presentations or meeting minutes associated with CTB teleconferences are posted on the CTB website.

The CTB “Meeting & Annual Reporting Calendar” for FY06-07 appears in Appendix E.

5.5 Reports

Science Plan and Implementation Strategy (SP&IS) Updates

The CTB SP&IS document will be updated on an annual basis, normally early in the calendar year.  The schedule depends on incorporation of the following input:

- TPT Progress Reports

- SAB review of SP&IS and TPT reports

- Annual SAB meeting written report

- CTB response to SAB

The CTB “Meeting & Annual Reporting Calendar” for FY06-07 appears in Appendix E.

Transition Project Team Progress Reports

Each of the TPTs prepares a progress report prior to the annual SAB meeting that includes an overview of accomplishments on science experiments (mapped against plans), computer usage, expected impact on operations, and future plans.   These reports are provided to CTB Management and to the SAB prior to annual SAB meetings.

Annual Reports

The CTB Management Team will prepare an Annual Report summarizing CTB activities during the previous year.  The report is evaluated by the OB, and then forwarded to the Directors of NCEP and the NOAA Climate Program Office.  The CTB Annual Report will generally be available early in the calendar year.

  - Webpage

The CTB webpage (www.cpc.ncep.noaa.gov/products/ctb) provides an overview of the CTB, including current activities, Announcements of Opportunity, CTB personnel, documentation, calendar, organization, directory, meetings, etc. Users are strongly encouraged to contact the CTB webmaster (Viviane.Silva@noaa.gov) or CTB Management (Wayne.Higgins@noaa.gov) with questions or suggestions for the CTB webpage.

APPENDIX A.  Research to Operations Guidelines

The CTB “Research to Operations (R2O) Guidelines” establish the path to implementation of changes in the NCEP operational climate model suite.   They establish the roles and responsibilities of the “home research institution” and the CTB in this process.  Significant resources for the home research institution and the CTB are required to carry out smooth transitions.  The R2O Guidelines, which indicate the path to implementation of changes in the NCEP operational climate model suite, consist of the following seven steps:

- Model development and refinement

- Preliminary assessment

- Calibration

- Interface with operations

- Final skill assessment

- Parallel tests

- Approval

While most of the steps are identical to the way EMC implements a majority of the changes in other suites of models, the calibration step is unique to the climate model suite. Some of the changes may not need to go through all of the steps. The three NCEP center directors (NCO, EMC and CPC) will have to approve changes to the procedures. In the end, the NCEP director will make the final decision to approve a change. Details of each step are described below.

1 	Model development and refinement

The key issue is additional, independent information to supplement operationally available products. The development and refinement are to be performed at model host institutions. For funded transition projects with a commitment of computer resources from the Climate Test Bed (CTB), the CTB computer resource will be used.

For tier-1 systems: Make 30- to 50-year CMIP (Coupled Model Intercomparison Project) runs, for comparison with the NCEP CFS, to demonstrate improved simulation of the seasonal-to-interannual (El Niño/Southern Oscillation) and intraseasonal (Madden-Julian Oscillation) signals, and a set of 1-year retrospective forecasts for January, April, July, and October for 1981-present (with a 30-member ensemble) to demonstrate skill in addition to the CFS benchmark.

For tier-2 systems: Make a set of 1-year retrospective forecasts for January, April, July, and October for 1981-present (with an ensemble of 30 or more members) using predicted SST from operational dynamical model retrospective forecasts from NCEP, other operational centers (when such forecasts become routinely available to NCEP), or one of the CPC statistical SST forecasts to demonstrate skill in addition to the CFS benchmark.

For modifications to the CFS model, the general guideline is that the changes must first be implemented in the NCEP Global Forecast System (GFS). This means that the model changes will be evaluated in both the weather and the climate arena. EMC has a well-established evaluation criterion on model changes so a close working relationship with the EMC staff is important.  Evaluation tools under development by CPC and its partners on the CTB will be used to decide on the added value of each new model.

RESOURCES: The development and refinement are to be performed at the model host institution.  AO-driven projects may seek computing resources from the CTB using the NOAA “Red” computer.  Retrospective forecasts are expensive and are currently not part of the resources allocated to either NCEP or the CTB, so developers need to work with NCEP to ascertain the necessary resources.

NCEP participation: EMC scientists should participate in projects involving model changes while CPC scientists should participate in projects involving evaluations and product development from the start of the project.

2	Preliminary assessment

Participants on the CTB should provide the complete retrospective forecast results (including raw monthly-mean fields) to NCEP and work with CPC and EMC to assess whether additional, independent information from the retrospective forecasts exists in relation to existing operational dynamical and statistical predictions. Iterations back to Step 1 may be necessary if the results do not provide the additional, independent information.

Statistically significant improvements obtained by the above steps would lead to an initial plan for implementation. A team of scientists from the external institution, CPC and EMC will work together to make the decision to go forward or iterate back to step 1.

RESOURCES:  CTB AOs will provide limited resources for preliminary assessment activities.  These projects will be competitive and peer reviewed.  The CTB will provide computer resources and system support for funded projects.  A plan for transition to operations at NCEP will be written and approved by NCEP and NWS management.  The plan must include personnel and infrastructure (desktop computing, travel, training, etc) resources for operational maintenance and enhancement as well as computing (cpu, disk, dissemination, archive).

NCEP participation: The team of scientists will report to the directors of NCO, EMC, CPC and CTB on the results of the preliminary assessment and seek their approval to initiate the implementation. NCO Production Management Branch will initiate an implementation plan and track the progress of the plan upon the approval of the directors.

- Calibration

Participants on the CTB should provide the complete 1 year retrospective forecasts for the period 1981-present for all calendar months (with an ensemble of 30 or more members).

RESOURCES: The resources needed to complete such runs are very large. For major projects such as multi-model ensembles and regional climate models, the host model institution will provide the necessary resources. Additional resource needs at NCEP will have to be proposed and planned for well in advance of the calibration step.

NCEP participation: Collaborate with CPC and EMC to continue the skill assessment for these forecasts and to perform cross-validation. The key consideration will be the usefulness of the forecasts in providing independent, additional information to the products that are already operationally available.  This includes whether a new product improves on the multi-model ensemble in US-temperature and precipitation prediction and whether it is at least as good as statistical/empirical methods.

- Interface with operations

As the calibration and assessment work is completed, the provider will work with EMC and NCO to make all programs in the model comply with NCO standards and to make all model output comply with WMO and NCO standard formats.

RESOURCES: CTB AOs will provide limited resources for developing the interface with operations.  These projects will be competitive and peer reviewed.  The CTB will provide computer resources and system support for funded projects.

NCEP participation: EMC and NCO will assess the additional computer resources needed to put the runs into the operational job stream. The model provider will work with NCEP to obtain additional resources needed for the operational runs of new systems.

- Final skill assessment

As the calibration runs are completed and the interface with operational standards is finished, CPC and EMC will work with the provider to complete the final assessment to determine if the change is ready for implementation. Assuming production resources are available for the additional runs, the parallel tests will begin.

RESOURCES: NCEP will provide the resources for this step.

NCEP participation: EMC and CPC will participate in all aspects of the final assessment.

- Parallel tests

EMC staff will work with the code provider and NCO to bring all running scripts up to NCO production standards.  NCO staff will run the new model in the parallel production environment and make routine near-real-time forecasts. CPC, EMC and the provider will verify that the parallel prediction products are the same as the provider intended. CPC forecasters will begin to evaluate the products in preparation for operational ISI forecasts.

RESOURCES: NCEP will provide the resources for this step.

NCEP participation: EMC and CPC will participate in all aspects of the final assessment.

- Approval

NCO Production Management Branch staff will brief the director of NCEP on the technical evaluation of the new model. EMC Global Climate and Weather Modeling Branch staff will brief the director of NCEP on the scientific evaluation of the new model, and the CPC Prediction Branch staff will brief the director of NCEP on the operational evaluation of the forecasts from the new model.  Four categories will be considered and checked off before the briefing takes place: 1) Forecast/analysis benefits; 2) Efficiency Assessment (especially important for NCO and CPC); 3) Compatibility with NOAA/NCEP IT assets; 4) Sustainability. Upon approval by the NCEP director, the new model will be scheduled for implementation in the NCEP production suite.

A.1 Testing Changes in (Atmospheric) Parameterizations in the GFS/CFS

For a proposed model change, make a set (3-4) of 45-day runs of the control and the new parameterization in the GFS using observed Sea Surface Temperature (SST) for January and July conditions. These runs are used to study the impact of the new parameterization (in a global sense) on the atmospheric circulation and various known model biases.  If one finds gross problems with the new parameterization in these runs, then one will need to diagnose the problems and go back to the parameterization formulations to identify ways to alleviate the problems.

Computing resources for the runs should come from the modelers own institution. For CTB supported activities, CTB computer resources are also available.

1. Make several CFS runs with the control version of the CFS and with the new parameterization for one year. Compared to the runs in 1), these runs should reveal more about impact of the parameterization in the coupled model world. Special attention should also be paid to the transients generated in the model versus those generated in the control run. This is a key step in assessing the impact of changes in parameterizations in the CFS for seasonal forecasts. Extensive diagnoses will be performed to ensure that the new runs will not degrade the coupled model climate. Computing resources for the runs should come from the modelers own institution. For CTB supported activities, CTB computer resources  are also available.

2. Put the new parameterizations in the current operational version of the GFS and perform a low-resolution global data assimilation system (GDAS) test for two months each for northern winter and northern summer using a version of the GFS at the resolution envisioned for the next version of CFS. There will also be a set of 10-day ensemble forecasts for each day of the assimilation.  The forecast skill will be evaluated using both deterministic and probabilistic measures. The new parameterization must not degrade the forecast skill of the current operational GFS.

These runs should be made collaboratively with the EMC transition team. Computing resources for the runs may either come from the CTB computer or the EMC computer.

3. When the tests are positive, perform 1-2 40-year free runs of the CFS to compare the interannual tropical Pacific signal to ensure that the new parameterization does produce a robust interannual signal in the tropical Pacific. Computing resources should come from the CTB computer.

4. Pending positive results from the steps above, add the new parameterizations into the GFS parallel test schedule to allow for a full resolution parallel test for a select period. In addition, make full resolution parallel tests for a chosen hurricane season and work with the Tropical Prediction Center to ensure that the hurricane track predictions from the parallel tests are acceptable to the hurricane specialists.  Computing resource for these runs will come from the EMC computer.

5. Pending successful outcome of the tests above, seek approval from NCEP Director for implementation in the GFS. In addition, the new package will be included in the next CFS model when tests of the new model begin. The new CFS will be taken from a version of the operational GFS that has been running for at least six months (for code maturity). Computing resource for the CFS upgrade will have to be planned by EMC and CTB since the resource needed is very significant.

APPENDIX  B.  Operations to Applications Guidelines

The Operations to Applications (O2A) guidelines discussed here provide the path to implementation of operational models in CPCs consolidated seasonal forecasts. Forecast models which are admitted to the consolidation must be accompanied by fairly-conducted hindcasts with the following qualities:

1. There must be reproducibility of retrospective forecasts made on the host computer to forecasts made on the NCEP computer. This is important for the application of calibration and weights for consolidation (which are derived from the retrospective forecasts) to real time forecasts which will be made on the NCEP computer.

2. Retroactive runs from each (initial) month during 1981-present for leads 1, 2, 3, 4, 5 etc. It is important that the retroactive runs are organized so as to be used optimally in operational real time forecasts. Forecasts runs from initial conditions past the 10th (of January say) cannot be used for the lead 1 FMA forecast. The number of members in the ensemble is up to the provider, but has to be at least 5.

3. Output variables must include: seasonal mean 2-meter temperature, precipitation, for US (including AK and HI; forecasts for other US interests are appreciated), global monthly mean fields of seasonal mean SST and, 850 and 200mb winds and 500-hPa heights.

4. The retroactive forecasts should be provided as total fields (i.e. not anomalies). CPC will use the normal (currently 1971-2000) it sees fit.

# 5. The latest runs should be available by the 10th of each month. The real-time system (model, input data etc) has to be identically the same as the frozen system that generated the hindcasts.

6. CPC will do a systematic error correction (each tool separately) and determine the regression coefficients under a three-years-out Cross-Validation approach. CPC will update the results each month.

7. If the weight assigned to a method is near zero, then we will redo the consolidation without that method and notify the originators of the method.

8.  We require at least 5 members in the ensemble.  The number of leads is up to the provider.

Appendix C: Management Structure and Terms of Reference

The CTB includes a Director, a Deputy Director for Administration, a Deputy Director for Transition to Operations, an Oversight Board (OB), a Program Manager, an Administrative Staff, a Climate Science Team (CST), Transition Project Teams (TPTs) and a System Support Team (SST).  Personnel consist of civil servants, contractors, visiting scientists and students.  An external Science Advisory Board (SAB) provides scientific advice and reviews CTB activities annually.  The CTB Organization is summarized in Figure C1.

Figure C1.  Organization of the NOAA Climate Test Bed facility.

Complete Terms of Reference for CTB Personnel, Boards and Teams are as follows:

CTB Director

The CTB Director shall be a civil servant selected by the NCEP Director in consultation with the OB.  The responsibilities of the CTB Director are to:

- Provide scientific leadership and generate CTB activities to carry out the CTB mission;

- Manage and administer the CTB in a manner consistent with NOAA policies and guidelines;

- Identify and allocate resources for support of CTB activities, including computer resources and sponsorship by the NOAA Climate Program Office;

- Establish Annual Operating Plans (AOPs) that map resources onto expected results and related deliverables;

- Develop GWPS Workplans and evaluate CTB personnel;

- Work with the CTB Program Manager(s) to coordinate activities across agencies; and

- Prepare the annual report summarizing CTB yearly activities and present the results to the OB.

CTB Deputy Directors

The CTB will have a Deputy Director for Administration and for Transition to Operations.  The CTB Deputy Directors shall be NOAA Civil Servants selected by the NCEP Director in consultation with the Oversight Board.

The responsibilities of the CTB Deputy Director for Administration are to:

- Assist the CTB Director and the CTB Program Managers in the day-to-day management of the CTB;

- Assist the CTB Director in preparing the Annual Operating Plan (AOP) for transition activities, infrastructure, deliverables, schedule, and budget.

The responsibilities of the CTB Deputy Director for Transition to Operations are to:

- Work with NCEP Central Operations (NCO), the operational centers and the principal investigators to negotiate the needs, milestones and timelines for transition to operations;

- Work with the CTB Director and the operational centers, to identify climate-related data, climate forecast products, and numerical/statistical modeling needs and coordinate these with the OB, CST, TPTs and other testbed directors to accomplish appropriate transitions to operational guidance products.

## CTB Program Manager

The CTB Program Manager (PM) will be from the NOAA Climate Program Office. The functions of the PM are to:

- Work with the CTB Management and the SAB to determine science priorities and the scientific direction for competitive Announcements of Opportunity (AOs);

- Conduct the merit review process for AO proposals, and make funding decisions in consultation with the CTB Management;

- Execute AO awards to Principal Investigators (PIs);

- Work with CTB management to continue post-award management of PIs;

- Coordinate with other NOAA Climate Program activities;

- Work with the CTB Management and the SAB to ensure coordination with National and International climate research programs; and

- Assist the CTB director in preparing the annual report to the OB.

## Administrative Staff

A Secretary will handle office duties such as travel, logistics for visitors and staff, messaging and other communications.  A Program Assistant will work on presentations, program plans and other documents.

The Oversight Board

The responsibilities of the OB are to:

- Report and make recommendations to the NCPO Director, and the NCEP Director concerning the CTB on an annual basis;

- Facilitate and sustain cooperation between NOAA and other sponsoring institutions;

- Review and approve the policies, research and development themes and priorities of the CTB;

- Adopt and revise, as appropriate, the Terms of Reference (ToR) for the operation of the CTB;

- Recommend to the NOAA Climate Program Office inclusion of other institutions in the CTB; and

- Meet at least twice a year.

The OB shall include the following members:

- The NCEP Climate Prediction Center (CPC) Director;

- The NCEP Environmental Modeling Center (EMC) Director;

- The Director for Research of the Earth System Research Laboratory (ESRL);

- The Director of the NOAA Geophysical Fluid Dynamics Laboratory;

- The Director of the International Research Institute for Climate Prediction;

- Appropriate representatives of other stakeholders.

The NCEP Director and the NCPO Director shall be invited to OB meetings (if available).  Occasionally they will be asked to make executive decisions when the OB cannot reach consensus.

The Climate Science Team

The Climate Science Team (CST) is composed of technical experts from NOAA organizations (e.g. CPC, EMC, CDC, GFDL) and other active Numerical Forecast Centers (NFCs) in the CTB (e.g. IRI, NCAR, NASA, COLA, ECPC). As a Team, the CST will have broad experience in the climate forecast problem, modeling issues, and product generation. 

Recommendations for new members of the CST can be made by the CTB Director, Deputy Directors, and current members of the CST. Membership is voted on by the CST, and approved by the OB. In view of EMC’s and CPC’s essential roles in the CTB, they are each given three permanent slots. All members of the CST will have a three-year term (except 3, 4 and 5 years initially to allow for a smooth rotation). Members who have rotated out can, after a minimum of one year, be invited back on the team. All externally funded CTB project PIs are required to become a member of the CST. In addition to the 6 EMC/CPC members and the external PI members, there will be 7 other members that are external to EMC and CPC. 

CST members will choose Co-Chairs (one internal to NOAA and one external to NOAA) who will have two-year terms. The Co-Chairs will rotate among different CST members.

The CST will:

- Guide CTB activities at the working level;

- Work with the TPTs to rank, monitor and track CTB experiments aligned with CTB objectives and resources;

- Provide advice on CTB contributions to the development path for NOAAs operational climate forecast systems and products;

- Monitor and evaluate results of CTB activities;

- Make recommendations to the CTB Director on computing resource usage priorities, and computing access policies; and

- Meet at least quarterly.

## Transition Project Teams

The CTB Transition Project Teams (TPTs) are the functional core of the CTB.  In particular, they are responsible for coordinating and completing CTB Project activities.  In addition, they enhance collaboration between internal and external participants on the CTB.  TPT membership includes CTB personnel, other NCEP employees, other NOAA employees, contractors, external PIs from competitive research programs (including Focal Points (FPs) chosen for each model and product supported by CTB), and members of the user community.  Each TPT has a Chair (or co-Chairs), who is (are) appointed by CTB Management to lead the team and to report progress to the CTB management and the CST as necessary.  CTB PIs are required to join a TPT in order to ensure that their activities are included, especially when computing resources are involved.

Specific functions of TPTs are to:

- Facilitate collaboration between internal and external participants on the CTB;

- Propose, coordinate and complete CTB transition project activities;

- Report progress to CTB management and the CST;

- Train outside users of CTB-supported software, including forecast systems, and products;

- Coordinate with CTB product developers and with forecast operations and applications activities.

The TPTs are not fixed in time and will naturally evolve to reflect the balance of internal (base funded) and competitive (AO-driven) activities on the CTB.  TPTs may be combined, expanded or eliminated to align with CTB programmatic and science priorities.

System Support Team

CTB System Support Team (SST) personnel will include Technical Assistants (TAs), System Administrators (SAs) and Information Technology (IT) specialists to

- Support external users on NCEP’s Supercomputing Cluster;

- Support users of CTB software, including the NOAA operational Climate Forecast System components, by providing code, scripts, computing information, training and debugging services;

- Request new accounts as required;

- Work with NCEP Central Operations (NCO), manage on-line and archive storage, including file organization and quotas, and act as a liaison to NCOs system administrators for CTB computing;

- Manage access to NCEP’s climate information, including calibration runs, and work with EMC system administrators to put CTB output on NOMADS servers;

- Provide IT support for CTB PCs and workstations;

- Maintain the CTB Web page.

TAs may be contractors in the CTB, in other NOAA line offices or in other organizations.

Visiting Scientists

Visiting scientists and post-doctoral fellows from other organizations such as NSF, NCAR, Universities and foreign organizations (e.g. international desks) will participate in CTB transition projects.  These visitors will be supported by their home institutions or by grants sponsored by NOAA or other agencies.  Visiting Scientists can include postdoctoral candidates and graduate students.

Science Advisory Board

Independent scientific advice is provided by a Science Advisory Board (SAB).  The SAB will work with the broader scientific community to recommend and review progress on high-priority scientific challenges for NOAA Mission Goals related to climate prediction and to review implementation strategies to meet these scientific challenges.  The SAB should consider coordination between the CTB and existing National and International programs (e.g., CLIVAR, GEWEX) to ensure that CTB efforts are consistent and up to date with current scientific understanding, and to ensure that long-term investments in climate research are available to the CTB.  SAB membership will include working scientists from a broad spectrum of national and international organizations including experts from active Numerical Forecast Centers.  The SAB membership will have a 3 year rotation (except 3, 4 and 5 years initially to make the rotation work).  The SAB will be chaired by a member of the non-NOAA Climate Community.  SAB membership will be recommended by the SAB chair and approved by the OB.  The SAB advises the CTB management and reports to the OB.  The SAB will meet at least once a year and will write a report to the CTB management following the meeting.  The SAB currently has 10 members, including the Chair.

Science Management Team

CTB competitive (AO-driven) projects go through the normal merit review process.  This begins with the submission of a Letter of Intent (LOI) to the Program Manager.  The Program Manager, in consultation with the CTB Science Management Team, identifies LOIs that fit CTB Science Priorities and then contacts PIs to encourage or discourage a full proposal.  The CTB Science Management Team has the following members: CTB Director, CTB Deputy Directors, CTB Program Manager, CPC Director, EMC Director, CPC Development Branch Chief, CPC Operations Branch Chief, EMC Climate Modeling Branch Chief.

Appendix D.  Proposed Time-Line for the next

CFS implementation in January 2010

- October 2006: In anticipation of the operational implementation of the sigma-p version of the GSI. Start testing this version for particular years in the 1979-2006 period where satellite changes would lead to new corrections to the radiances. Run the GSI for a few random years and save the fluxes for the next bullet.

(Saha, Treadon, van Delst, Derber, Kliest, Woolen, Pan, Kistler, White)

- June 2007: In anticipation of the ESMF version of the coupler and MOM4. Start testing the new GODAS (with MOM4 and seaice) and GLDAS with fluxes obtained from atmospheric GSI analyses of some random years (see bullet above).

(Behringer, Sheinin, Wang, Wu, Nadiga, Stokes, Pan, Moorthi, Grumbine, Saha, Mitchell, Meng, Wei)

- August 2007: In anticipation of the operational implementation of the next GFS. Start pilot studies with the first “prototype” of the fully coupled CFS reanalysis, which will include the GSI (with new GFS), GODAS and GLDAS.

(Saha, Pan, Iredell, Derber, Behringer, Mitchell, Meng, Yang, Moorthi, Treadon, Sheinin, Woolen, Kistler, White)

- January 2008: Begin Production and Evaluation of the CFS Reanalysis for the full period from 1979 to 2007 (29 years)

(Reanalysis Team: Saha, Thiaw, Wang, Nadiga, Wu, Lu.

Evaluation Team: EMC and CPC Personnel)

- July 2008: Begin running CFS Retrospective Forecasts for 2 initial months: October and April, and evaluate the monthly forecasts as well as the seasonal Lead-1 DJF and JJA forecasts.

(Hindcast Team: Saha, Thiaw, Wang, Nadiga, Wu, Lu.

Evaluation Team: EMC and CPC personnel)

- January 2009: Operational Implementation of the CFS Reforecasts (for the rest of the 10 calendar months) in the proposed slot of REFCST in the production suite. (NCO personnel, Saha, Moorthi, Pan, Behringer)

- November 2009: Begin computing calibration statistics for CFS daily, monthly and seasonal forecasts. Prepare CFS Reanalysis and Retrospective Forecast data for public distribution.

(Saha, Thiaw, CPC personnel)

January 2010: Operational implementation of the next CFS monthly and seasonal forecast suite.

Appendix E. Contact Information

Wayne Higgins 
CTB Director
CPC Principal Climate Scientist
e-mail: Wayne.Higgins@noaa.gov

Hualu Pan 
CTB Deputy Director for Transition to Operations
Global Climate and Weather Modeling Branch Chief
e-mail: Hualu.Pan@noaa.gov

Mel Gelman 
CTB Deputy Director for Administration
Climate Prediction Center                                                                                                     e-mail: Melvyn.Gelman@noaa.gov

Kenneth Mooney 
CTB Program Manager
NOAA Office of Global Programs
e-mail: Kenneth.Mooney@noaa.gov

Viviane Silva 
CTB Webmaster
e-mail: Viviane.Silva@noaa.gov

Appendix F.  Acronyms

The following is a list of acronyms used in the text:

AO  		Announcement of Opportunity

AOP  		Annual Operating Plan

CA  		Constructed Analog

CCA  		Canonical Correlation Analysis

CDC  		Climate Diagnostics Center

CDEP  	Climate Dynamics and Experimental Prediction

CEOP  	Coordinated Enhanced Observing Period

CFS  		Climate Forecast System

CLIVAR  	Climate Variability and Predictability

CMIP  		Coupled Model Intercomparison Project

COLA  	Center for Ocean Land Atmosphere Studies

CONS  	Official CPC Consolidated Forecast

CPC  		Climate Prediction Center

CPI  		Climate Predictive Index

CPPA  	Climate Prediction Program for the Americas

CPT  		Climate Process and modeling Team

CST  		Climate Science Team

CTB  		Climate Test Bed

C&GC  	Climate and Global Change

DOD  		Department of Defense

DRI  		Desert Research Institute

EMC 		Environmental Prediction Center

ENSO  	El Niño Southern Oscillation

ESMF  	Earth System Modeling Framework

ESSIC  	Earth System Science Interdisciplinary Center

FP  		Focal Point

FTE  		Full Time Equivalent

FY  		Fiscal Year

GAPP 	 	GEWEX Americas Prediction Program

GEWEX 	Global Energy and Water Cycle Experiment

GFDL  	Geophysical Fluid Dynamics Laboratory

GFS  		Global Forecast System

GMAO  	Global Modeling and Assimilation Office

IRI  		International Research Institute

ISI		Intraseasonal-to-Interannual

IT  		Information Technology

JCSDA  	Joint Center for Satellite Data Assimilation

LOI  		Letter of Intent

M&OP		Management and Operations Plan

MESA 	Monsoon Experiment South America

MJO  		Madden Julian Oscillation

MOM  	Modular Ocean Model

NAME  	North American Monsoon Experiment

NASA  	National Aeronautics and Space Administration

NCAR  	National Center for Atmospheric Research

NCDC  	National Climatic Data Center

NCEP  	National Centers for Environmental Prediction

NCO  		NCEP Central Operations

NCPO  	NOAA Climate Program Office

NFC  		Numerical Forecast Center

NOAA  	National Oceanographic and Atmospheric Administration

NOMADS  	NOAA Operational Model Archive and Distribution System

NSF  		National Science Foundation

NTOP  	NCEP Technical Operating Plan

NWS  		National Weather Service

OB  		Oversight Board

OGP  		Office of Global Programs

OHD  		Office of Hydrology

PACS  	Pan American Climate Studies

PI  		Principal Investigator

PMEL  	Pacific Marine Environmental Laboratory

P&P  		Predictions and Projections

QC 		Quality Control

R&D  		Research and Development

RSIS  		RS Information Systems

SA  		System Administrator

SAB  		Science Advisory Board

SST  		Sea Surface Temperature

SST 		System Support Team

S-to-I  		Seasonal-to-Interannual

SP&IS  	Science Plan and Implementation Strategy

SWG  		Science Working Group

TA  		Technical Assistant

TPT 		Transition Project Team

VAMOS  	Variability of the American Monsoons

VOCALS  	VAMOS Ocean Cloud Atmosphere Land Study

WMO              World Meteorological Organization